Project Planning Phase

Project Planning Template — Product Backlog & Schedule

| Date | 12-10-2026 |
| --- | --- |
| Team ID | Individual participant - 323103312124@gvpce.ac.in |
| Project Name | Software Installation Request - ServiceNow |
| Maximum Marks | 5 Marks |

# Planning basis

This plan follows the repository's documented implementation sequence rather than imposing arbitrary Scrum dates. The repository describes requirement analysis and update-set preparation, backend data/workflow configuration, catalog UI/UX, testing and migration, then deployment documentation. Sprint labels and story points below are planning estimates for organizing the work; the supplied ZIP does not include a verifiable Git commit history or actual sprint records.

# Product Backlog, Sprint Schedule, and Estimation

| Sprint | Functional Requirement (Epic) | Story No. | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Phase 1 | Requirements & data model | USN-1 | As an administrator, I want the request scope and core table relationships defined so the build has a clear baseline. | 2 | High | Individual |
| Phase 1 | Update Set baseline | USN-2 | As an administrator, I want the initial configuration packaged in an Update Set so it can be tracked and moved. | 2 | High | Individual |
| Phase 2 | Catalog data architecture | USN-3 | As the workflow, I need Requested Item and Catalog Task fields/relationships configured to retain request context and assignment. | 3 | High | Individual |
| Phase 2 | Business Rules | USN-4 | As the system, I need the configured Requested Item rule to run on the relevant Pending-state transition. | 2 | Medium | Individual |
| Phase 2 | Approval automation | USN-5 | As a manager, I need the catalog request routed to me for approval so the business need is reviewed before fulfillment. | 5 | High | Individual |
| Phase 2 | Approved fulfillment | USN-6 | As the fulfillment team, I need a linked Catalog Task assigned to Software after approval so approved work has clear ownership. | 3 | High | Individual |
| Phase 3 | Catalog item & variables | USN-7 | As an employee, I want a Software Installation Request catalog item with software name, version, justification, and urgency fields. | 3 | High | Individual |
| Phase 3 | Usability & portal | USN-8 | As an employee, I want required-field validation, help text, and portal search/status access so I can submit and track a request. | 3 | High | Individual |
| Phase 4 | End-to-end validation | USN-9 | As a tester, I want to verify REQ/RITM/SCTASK linkage, approval routing, task assignment, and configured email generation. | 5 | High | Individual |
| Phase 4 | Update Set migration | USN-10 | As an administrator, I want the update set completed, exported, previewed, and committed in a target instance to check migration readiness. | 3 | Medium | Individual |
| Phase 5 | Setup manual & handover | USN-11 | As a reviewer, I want setup instructions and implementation screenshots so the solution can be recreated and demonstrated. | 2 | Medium | Individual |

# Phase-level schedule (sequence-based; not historical sprint dates)

| Phase | Repository-backed work package | Dependency / exit condition | Planned story points |
| --- | --- | --- | --- |
| Phase 1 | Requirements, scope, stakeholder roles, table mapping, baseline update set. | Scope and core records identified before configuration. | 4 |
| Phase 2 | Data architecture, Business Rules, Flow Designer approval and task creation. | Approval and task path ready for catalog integration. | 10 |
| Phase 3 | Catalog item, variables, mandatory validation, tooltips, portal search and status. | Employee can submit and track a request. | 6 |
| Phase 4 | End-to-end checks, record linkage, email logs, update-set export/import. | Core request path and migration package checked. | 8 |
| Phase 5 | Setup manual, screenshots, deployment documentation and presentation. | Recreation and handover materials prepared. | 2 |
| Total | Sequence reflects the repository's five implementation phases. | Estimates only; actual velocity is not available. | 30 |

Project Tracker, Velocity & Progress Review

The template asks for actual sprint start/end dates, completed story points, release dates, velocity, and a burndown chart. The supplied repository ZIP documents implementation phases and screenshots but does not provide dated sprint records or a daily task log. Therefore, actuals are marked “Not recorded in supplied evidence”; no historical dates or completion metrics are fabricated.

# Project tracker

| Work package | Planned points | Duration | Start date | End date | Points completed | Release date |
| --- | --- | --- | --- | --- | --- | --- |
| Phase 1 | 4 | Not recorded | Not recorded | Not recorded | Not recorded | Not recorded |
| Phase 2 | 10 | Not recorded | Not recorded | Not recorded | Not recorded | Not recorded |
| Phase 3 | 6 | Not recorded | Not recorded | Not recorded | Not recorded | Not recorded |
| Phase 4 | 8 | Not recorded | Not recorded | Not recorded | Not recorded | Not recorded |
| Phase 5 | 2 | Not recorded | Not recorded | Not recorded | Not recorded | Not recorded |
| Total | 30 | — | — | — | Not recorded | Not recorded |

# Velocity calculation

Velocity is the number of story points completed in a sprint. Since actual completed points and sprint durations are not present in the supplied repository, actual velocity and average velocity cannot be calculated responsibly. For future tracking, use:

Velocity = story points completed in the sprint

Average velocity = total completed story points ÷ number of completed sprints

# Progress / burndown handling

No burndown chart is included because a truthful chart requires daily remaining-work data or sprint-level actuals, neither of which is present in the repository ZIP. This follows the instruction to avoid generic bar graphs and prevents presenting invented progress as project evidence.

# Repository evidence used

| Repository artifact | Planning evidence derived |
| --- | --- |
| Phase 1 README | Requirements, stakeholders, scope, table mapping, and update-set baseline. |
| Phase 2 README | Data architecture, Requested Item business rule, Flow Designer approval and task creation. |
| Phase 3 README | Catalog item, software_name/version_required/license_justification/urgency variables, portal navigation, validation and status. |
| Phase 4 README | Flow-to-catalog binding, sc_request/sc_req_item/sc_task linkage, update-set export/import, end-to-end verification. |
| Phase 5 README + SETUP_MANUAL | Deployment/recreation steps and screenshots for catalog setup, Flow Designer, portal submission, task assignment, and email logs. |

# Implementation evidence (repository screenshots)

Selected screenshots from the repository illustrate the real configuration artifacts behind the plan:

Catalog item form — UI/UX configuration

Flow Designer canvas — approval and automation

# Planning note

Story points are relative estimates for organizing the documented work, not values from a recorded planning meeting. The phase ordering is based on the repository's implementation documentation. To convert this into a historical tracker, add actual Git commit dates, sprint boundaries, and verified completed work.